## Increment
INCREMENT

			MoSCoW	SH	C	W
TB1	Description	Estimation	M	S	C	W
Setup of the project	Create project structure and setup redux.	3 hours	x
Header& Footer	Create header and footer.	4 hours	x
Login	Create login layout.	2 days	x
Sign up	Create signup layout		x
Create users in json server	Create list of users in json server		x
Profile	Create profile layout	2 days	x
TB2	Description
Dashboard (Admin)	See Managers list (Admin)	2 days
Dashboard List(Manager)	Create dashboard that holds list of events to be validated.		x
Event List	Create events list for possible events to be created.	2 days	x
Edit Personal Information Layout	Create the edit personal information form		x
Event form + Apply for an event(user)	Create event form and apply for an event	1 day
TB3	Description
Accept/Decline event	Managers have the right to accept or decline a user reservation	3 days	x
Confirmed events list(User)	See event confirmation		x
Personal information(User,Manager,Admin)	Edit personal information	2 days	x
TB4	Description
Delete User(Admin)	Delete user profile	1 day			x
Delete Manager(Admin)	Delete manager profile				x
Finish About layout,Home Layout	Making final changes and design.	4 hours		x